## Gantt
Create a Gantt Chart in this worksheet. Enter title of this project in cell B1. Legend title is in cell I1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | UON ICT Services Portal Development Plan | [5 empty] | Legend:
Enter Company Name in cell B2. A legend is in cells I2 through AC2. | boisterous-bards | [5 empty] | On Track |  |  |  |  | Low Risk |  |  |  |  | Med Risk |  |  |  |  | High Risk |  |  |  |  | Unassigned
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell F3 or allow the sample formula to find the smallest date value from the Gantt Data table. Project Start Date: label is in cell D3. |  |  | Project Start Date: |  | 2019-05-23
A Scrolling Increment is in cell F4. Months for the dates in row 5 are displayed starting in cells I4 through cell BL4. Do not modify these cells. They are auto updated based on the project start date in cell F3. |  |  | Scrolling Increment: |  | 0 |  | May | [13 empty] | June | [27 empty] | July
Cells I5 through BL5 contain the day number of the month for the Month represented in the cell block above each date cell and are auto calculated. Do not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2019-05-23 to 2019-07-17
A scrollbar is in cells I6 through BL6. The increment for paging through the data is defined as 2 pages at a time and can be configured in the settings for the control bar. To jump forward or backward in the timeline, enter a value of 0 or higher in cell F4. A value of 0 takes you to the beginning of the chart.
This row contains headers for the project schedule that follows below them. Navigate from B7 through BL7 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I7 and continues through cell BL7. All project timeline charting is auto generated based on the category, start date and number of days entered in the Milestones table. | Milestone Description | Category | Assigned To | Progress | Start | No. Days | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Enter Project information starting in cell B9 through cell G9. Sample data is in cells B9 through G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | Core Logic
| Start Development This shall formulate the vital functionality of the Services Portal | Milestone | All Members |  | 2019-05-23 | 3 | bar: T to S
| User Interface A consistant theme (single CSS) with a style in theme with UON. - JSP and CSS implementation of the pages as suggested in the Presentation Diagram: 1. Homepage, 2. ArticlePage. (These are on the User end as shown in the Use case diagram) 3. Issue Category Page containing current maitainance progress issued appropriately (for the Support staff) 4. Error page | On Track | Da | 0% | 2019-05-26 | 7
| SQL Implementation with the Servlet - Setup communication between the Uni SQL database and and a basic servlet - Prefill the first database table with username-password-role triplets as per the assignment specification along with first name, surnace, email, contact number fields. Assign a state string too for later recall from the servlet. - a seperate knowledge-Base database table should contain the resolved issue for the user. | On Track | Ruan | 0% | 2019-05-26 | 7
| JAVA Beans, additional servlet logic and implementation to JSPs - Build upon the servlet in use with the database which forms the "System" - Write Java Beans for the logic of the JSPs - Ensure Interconnectivity between JSPs, Beans, Servlet, file structure, WEB XML etc - Implement serialisation and session tracking - Error reporting logic | On Track | Luke | 0% | 2019-05-26 | 7
| Validation and security implementation - This shall be implemented by any member with free time using tomcat's validation system - Constant Testing (Including hacking it on purpose) | On Track | All Members | 0% | 2019-05-28 | 12
Additional Requirements
| Begin enchancing the website with additional tasks Safe to move on to Additional Functionality that the Customer has suggested. | Milestone | All Members | 0% | 2019-06-02 | 1 | bar: S
| (Additional Task 3) Allow Users to Add comments to Knowledge-Base Articles - Weighted 10 | On Track | Da | 0% | 2019-06-02 | 7
| (Additional Task 19) Removability of user Photos - Weighted 10 | On Track | Ruan | 0% | 2019-06-02 | 7
| (Additional Task 8) Advertise planned/current maitenance - Weighted 5 (Additional Task 15) Sort issues by date they were reported - Weighted 5 | On Track | Luke | 0% | 2019-06-02 | 7
| Setup Github service for us to use. File Structure organisation. | On Track | All Members | 0% | 2019-05-26 | 10
Project Completed
| Finalise, test and submit completed work in the specified way the customer requested | Goal | All Members |  | 2019-06-09 | 1 | S: 2
NOTES:
People who have finished their work or have additional knowledge of a subject that another member is struggling with, please provide assistance and make a note of it in this document.
We must all meet at least once a week and maintain facebook communication whenever we can
Meetings shall occur at either 9AM Thursday or 9AM Friday. With Friday holding greater priority.
This was made using an excel template: 'Gantt Project Planner'. This was produced by Microsoft.
This is an empty row
This row marks the end of the Gantt milestone data. DO NOT enter anything in this row. To add more items, insert new rows above this one. | To add more data, Insert new rows ABOVE this one